## Progress Report
PROGRESS REPORT
| SoW Project Code | SOW/22E15 | Student Participants # |  | (paste your short signature jpeg here)
| Start Date | 2022-07-23 | Direct | 5
| End Date | 24/07/2022 | Indirect (Partial) | 0
| Project Location(s) | Murshidabad/ West Bengal
| Progress Report as on (Mention the current date) |  | 2023-02-17 |  | Soma Kumar
Tick the Relevant Boxes only
SN | ACTIVITIES DONE |  |  |  | Project is Complete | Yes
1 | Workshop on Responsible Tourism theme "Sustain N Serve" in association with the Murshidabad Tourism Welfare Society. This workshop was conducted by the students of MTTM 2021 - Kolkata along with two faculty members (Mrs. Soma Kumar & Mr. Anirban Roy of NIHTM-KOL. It was attended by twenty (20) local Tangawalas. The Following activities were performed during the workshop: |  |  |  | Project completed
2 | Awareness about safety norms during services |  |  |  | Project activity not started
3 | Briefing about the hygeine standards and maintaining those for better service delivery. |  |  |  | I have been communicating on my project internally | Yes
4 | Some important etiquette to be noted regarding guest service.
5 | Distribution of medical kits to the attendees |  |  |  | I have been communicating on my project also externally | Yes
6 | Distribution of participation certificates to the attendees
7 | Distribution of food packets to the attendees |  |  |  | I am now not ready to communicate on my project | Yes
8 | Visit to the the popular historical sites of Murshidabad on 2324.07.2022. The studetns got the chance to learn about the historical background of the city and the popular sites like Motijheel Park, Hazarduari Palace Museum, Katra Masjid, Kathgola Gardens, Khosh Bagh, House of Jagath Seth, Imambara, Tomb of Azimminisa Begum, etc.
9 |  |  |  |  | My students are ready to talk about the project | Yes
10
My students are not yet ready to talk the project
SN | OUTPUTS
1 | Tangawalas got acknowledged during the workshop |  |  |  | Local support has been far from satisfactory | Yes
2 | The attendees were able to bring up their concern areas
3 | The organizers (students) learnt about the survival challenges from the attendees |  |  |  | Local support has always been there and is adequate
4 | The organizing team was able to benefit the host community by generating revenue in the area.
5 | The attendees were glad to be part of the workshop and the head of the Tangawala Union also requested to conduct such workshops on large scale in near future. |  |  |  | Project participants are regularly involved | Yes
6 | The students got chance to learn ablout the popular historical sites
7 |  |  |  |  | Project participants are not regularly involved
8
9 |  |  |  |  | My students will be able to submit their reports for CA-2 | Yes
10
Any Other (REMARKS, if any)
This workshop was having prime focus on Responsible Tourism with the theme "Sustain N Serve". The workshop attendees were the Local Tangawalas in Murshidabad and the manifestation was about safety, hygeine, grooming, service etiquettes, etc.. The students also learnt about the various challenges faced by the Tangawalas and found a hope in them for support and sustain.

## Utilization Certificate
Final Settlement Form
(Print, attach supporting docs on expenses, your signature, approval signature of portal head and submit to F&A dept.)
SoW | Project Code: | SOW/22E15
| Grant Receipent NKC ID : | NKC 0415
| Location: | Kolkata
| Approved Budget: INR | 12000
A | Receipts | Amount
Date
| First Installment | 6000
| Second Installment | Not received
| Third Installment | 0
| Others | 0
| Total | 6000
B | Utilization | Amount
Details
Date
2022-07-23 | Onword Train Ticket | 558
2022-07-23 | Onword Train Ticket | 108
2022-07-24 | Return train Ticket | 558
2022-07-24 | Return train Ticket | 108
2022-07-21 | Banner | 288
2022-07-20 | Certificate to Tangawala | 500
2022-07-20 | Medical Kit to Tangawala | 2130
2022-07-24 | Tour Package rate for faculty (3215 x 2) | 6430
2022-07-24 | Refreshment to tangawala (130+10=140 x 18) | 2520
2022-07-24 | All spot entry fee | 700
2022-07-24 | Refreshment for students and faculty | 840
2022-07-24 | Tour Package rate for students | 5575
| Total | 20315
| Surplus/Deficit | -14315